How We Forecast Production

Rebuilt and validated against our own production history — June 2026

## 1.  The goal

- Reliably answer two questions: when will a job finish, and when can we start the next one.

- This month we rebuilt the forecaster and tested every assumption against our own history instead of guessing.

## 2.  How it works, in plain English

- When a job starts: the shop completes about $49,000 of work per week — our real, measured pace. Jobs are lined up in the owner’s priority order, so a start date ≈ the work ahead of it ÷ our weekly pace.

- When it finishes: history shows a job spends about 1.5–3 weeks on the floor, mostly driven by its size. We add that range to the start date.

- Every answer is a range (likely + worst-case), not a false-precise day. Jobs already on the floor are projected from how far along they actually are.

## 3.  Built only on data we trust completely

- Three numbers, each tied to a real event: when a job dropped into the shop, when it stacked, and its computer value. Nothing depends on guesswork.

## 4.  What we tried and dismissed (why the result is trustworthy)

- An hours-based model — we don’t track real labor hours, and it predicted finish dates worse than simply guessing the average.

- A capacity cap — the data shows we routinely run 12–14 jobs at once and start new ones into a full shop. There is no ceiling.

- Predicting starts from how busy we are — the wait to start a job had no relationship to how full the shop was.

- A department-by-department bottleneck model — the one we want, but today’s data can’t support it yet. Parked, not abandoned.

- What survived: the simple weekly-pace + size model — the most accurate of all, within about 4 working days on average.

## 5.  The data problem holding us back

- Department check-marks are entered in a batch at week’s end (a Thursday spike), not when the work actually happens. The final step is almost never marked at all.

- So we can see what happened, but not when during the week — which means we can’t yet measure which departments are fast and which drag.

## 6.  What better data reporting would unlock

- Using the same marks we already collect, but entered on time:

- Pinpoint the real bottleneck, and separate slow work from waiting in line — two different problems with different fixes.

- See which departments grow with job size (assembly, specialty) vs. stay flat (doors) — for smarter staffing.

- Tighten finish dates and forecast department-level load, not just whole-job timing.

Bottom line: the next gain isn’t software — it’s marking work as it happens.